## Read Me
How to use this resource
This planner and tracker is designed to help you structure and evaluate investor collaborations using clear, flexible, behaviourally-informed steps. Suggested timelines are examples only - feel free to adjust them to suit your context, whether a 2-month sprint or a 3-year engagement. What's inside? Planning Worksheet: Set timelines, assign responsibilities Progress Tracker: Track completion and gather feedback Recommended approach 1. Use the Planning Worksheet to define actions, adjust timing, assign leads 2. Use the Progress Tracker to check completion, gather updates and feedback 3. Revisit steps regularly to reflect and iterate | Flexible timelines No two collaborations are the same. Suggested timelines are just a guide: 2-month sprint: fast policy input 3-6 months: thematic focus or advocacy 1-2 years: deeper working group collaboration •3+ years: sectoral or global platform initiatives Behaviourally designed Each step includes: • Goal prompts – for clear, time-bound action • Nudges – to help teams follow through • Tracking – to support accountability and reflection

## Guide Reference
Step | Goal Prompt | Nudge | Track Progress | #VALUE!
1. Investor-led | Agree on and document your investor leadership structure within the first 3 months. | Use your kick-off meeting to start the leadership conversation. Assign someone to draft a proposal within 3–4 weeks. | By Month 3: Has a leadership model been agreed and documented?
2. Goal Alignment | Within 30 days of your first group meeting, agree on a written set of shared goals. | Create a shared 'Collaboration Charter'. Assign one person to draft and include finalisation in the next meeting. | By Day 30: Is the goal statement finalised and shared?
3. Governance | By Day 60, establish a governance framework (roles, decisions, legal if needed). | Use 15 minutes every second meeting to check in on governance setup and clarify roles. | By Day 60: Has a charter or terms of reference been approved?
4. Timeline & Tasks | Share a 12-month roadmap with task owners and check-in points within 45 days. | Use a shared tool to assign tasks and auto-reminders. Ask each owner to add a midpoint check-in. | By Day 45: Has the roadmap been shared?
5. Trust-building | Hold at least one informal trust-building activity each quarter. | Rotate a 'community connector' each quarter to plan and send invites. | Each quarter: Was an informal activity held?
6. Resourcing | By Month 3, secure at least one form of resourcing (staff, funding, or support). | Include a short 'resourcing spotlight' in your first 3 meetings to share opportunities. | By Month 3: Has a resourcing commitment been secured?

## Planning Worksheet
Step | Key Action | Suggested Timeline | User-defined Timeline | Assigned To | Notes | #VALUE!
1. Investor-led | Define and agree on leadership model | Within 3 months
2. Shared Goals | Develop goal statement and charter | Within 30 days
3. Governance | Set up governance structure | Within 60 days
4. Timeline/Tasks | Build collaboration roadmap | Within 45 days
5. Trust-Building | Plan informal trust-building activity | Quarterly
6. Resourcing | Secure core support (funding/staff) | By Month 3

## Progress Tracker
Step | Has this been completed? (Yes/No) | Notes or Evidence | Next Check-In Date | Survey/Feedback Score (if used) | Notes | #VALUE!
1. Investor-led | Define and agree on leadership model | Within 3 months
2. Shared Goals | Develop goal statement and charter | Within 30 days
3. Governance | Set up governance structure | Within 60 days
4. Timeline/Tasks | Build collaboration roadmap | Within 45 days
5. Trust-Building | Plan informal trust-building activity | Quarterly
6. Resourcing | Secure core support (funding/staff) | By Month 3